## Actions by issue
Battery ontology — remaining actions per GitHub issue
All 11 issues of CIRPASS-2/ontologies-battery are open as of 1 September 2026. One row per issue; done work is not listed. Red dependency = external blocker.
Issue | Issue title | Link | Remaining action | Waits on | Battery files | CORE side
#1 | Bind the battery carbon footprint (CF) to CORE (LCA/CONNECTOR/COMP) | https://github.com/CIRPASS-2/ontologies-battery/issues/1 | Once the LCA module enters the CORE: activate the 8 remaining deactivated shapes — incl. hasLCAStudy, where only the class is still missing — and replace the 2 active shapes with LCA-study shapes, since they constrain dpp:CarbonFootprint, which core#47 deprecates. Meanwhile, obtain the LCA module (lca-preview branch or Semantic Treehouse export) so the profile can be reviewed as a whole. Reconcile dpp:hasPerformanceClass with eudpp:carbonFootprintPerformanceClass (core#41), and flag that core#36 is reported closed while carbonFootprintLabel is absent. | LCA in CORE; core#41, #47, #52, #53, #54 | battery-cf-shapes.ttl | LCA module, connector.owl
#2 | Umbrella: add battery category (Art 2) — reuse CORE ClassificationCode | https://github.com/CIRPASS-2/ontologies-battery/issues/2 | Decide where the rated energy in kWh is declared — no term carries it today (ratedCapacity is in Ah, certifiedUsableBatteryEnergy is the UN GTR No 22 value, the CORE only has EnergyConsumption) — then activate the deactivated 2 kWh scope shape. | Marc-Andree's reply | battery performance.ttl, battery-shapes.ttl | p_dpp.owl or mat.owl
#3 | Umbrella: battery status and second-life passport linkage | https://github.com/CIRPASS-2/ontologies-battery/issues/3 | Deprecate bat:hasBatteryStatus (owl:deprecated + dcterms:isReplacedBy) once a cross-sectoral eudpp:productStatus lands; keep tracking core#56 (linkToPreviousDPP unidirectional, xsd:anyURI) and core#57 (dppStatus "Invalid" vs prEN 18223 "Marked-for-deletion"). | core#35 (+ #56, #57) | battery ontology.ttl, battery-statuses.ttl | p_dpp.owl
#4 | Umbrella: link to the supply-chain due-diligence report (Annex XIII Part C) | https://github.com/CIRPASS-2/ontologies-battery/issues/4 | Migrate bat:dueDiligenceReport and bat:dueDiligenceAudit to the eudpp:Source pattern — single pass with #11. Which LCA version prevails (Marc-Andree's, or the merge with Fatima Danash's) is for Carolynn and the module owners to decide. | LCA in CORE (#11) | battery ontology.ttl | LCA module
#5 | Umbrella: dismantling information, safety measures, test-report results and access-tier decision | https://github.com/CIRPASS-2/ontologies-battery/issues/5 | Migrate bat:dismantlingInformation, bat:safetyMeasures and bat:testReportResults to eudpp:Source (with #11); if core#39 lands, point to eudpp:testReportResults instead. (Access tiers: delivered in the 28 Aug SHACL views.) | LCA in CORE (#11); core#39 | battery ontology.ttl | LCA module, comp.owl
#6 | Performance: time dimension for BMS-updated (dynamic) parameters | https://github.com/CIRPASS-2/ontologies-battery/issues/6 | Awaiting Marc-Andree's review of batperf 0.3.0 — BatteryStateRecord, hasBatteryStateRecord, asOfDate and the 22 re-domained properties. No reply as of 1 September. | Marc-Andree's reply | battery performance.ttl | —
#7 | Performance: machine-readable units, datatype corrections, CORE anchoring | https://github.com/CIRPASS-2/ontologies-battery/issues/7 | Report on core#58 that 22 of the 36 batperf units have no SI Digital Framework IRI — exactly the battery-specific ones (%, %/month, Ah, kWh, year, A/Ah, W/Wh); redo the unit-annotation pass if OM-2 is chosen instead. | core#58 | battery performance.ttl | p_dpp.owl, LCA module
#8 | Labeling: split Cd/Pb symbols, controlled vocabularies, QR/data-carrier check, CORE re-anchor | https://github.com/CIRPASS-2/ontologies-battery/issues/8 | Open the CORE issue "IDENT: add a data carrier concept (QR code, barcode, NFC)", anchored on the ESPR data-carrier provisions and CEN/CLC JTC 24, and post its number in #8 — the #10 data-carrier shape is deactivated pending it. Then re-anchor batlab:BatteryLabel on the cross-sectoral Labelling class (core#55), and re-check the extinguisher-class vocabulary (class L of ISO 3941:2026, possible EN 2 amendment) at labelling-IA adoption. | none for the data carrier issue; core#55 and the labelling IA for the rest | battery-shapes.ttl, battery labeling.ttl, battery-extinguisher-classes.ttl | ident.owl, connector.owl, p_dpp.owl
#9 | Materials: subPropertyOf hasMaterial, controlled chemistry vocabulary, MAT two-level coordination | https://github.com/CIRPASS-2/ontologies-battery/issues/9 | On MAT v2: re-anchor batmat:BatteryChemistry (its anchor dpp:MaterialOfComposition disappears in the core#24 consolidation), map batmat:BatteryLocation onto the MaterialComposition (part) level, and add eudpp:materialTypeScheme to the ten chemistries (core#25). Re-check the ten chemistries and their notations at labelling-IA adoption. | core#24, #25 (MAT v2); labelling IA | battery materials.ttl, battery-locations.ttl, battery-chemistries.ttl | mat.owl
#10 | Deliver the anticipated SHACL shapes + an Annex XIII / long-list coverage matrix | https://github.com/CIRPASS-2/ontologies-battery/issues/10 | Push the 28 Aug SHACL deliverables (battery-shapes.ttl, the three per-audience view files, battery-access-tiers.ttl) to the repository and post the reply on #10 — two shapes deliberately deactivated as a checklist: the 2 kWh test of #2 and the data carrier of #8. | — | battery-shapes.ttl, view files, battery-access-tiers.ttl | —
#11 | Migrate documentation links to eudpp:Source once the LCA module is integrated into CORE | https://github.com/CIRPASS-2/ontologies-battery/issues/11 | Migrate the five documentation links in one pass (owl:deprecated + dcterms:isReplacedBy, then eudpp:hasExternalDocumentation to an eudpp:Source instance). First ask Marc-Andree how a due-diligence report, a dismantling manual or a test report get typed — the five Source subclasses (PCR, BackgroundDatabase, ComplianceSystem, ReviewReport, EPDDocument) cover none of them, and today the property name carries the type; also check the domain of hasExternalDocumentation. | LCA in CORE; Marc-Andree | battery ontology.ttl | LCA module